# MASCD Annual Meeting Checklist

| # Two Years in advance | # Who’s Responsible? |
| --- | --- |
| ☐ Host Region meets to select and recommend a person for the President to appoint as a chair for the meeting. (A coordinator may also be selected.) |  |
| ☐ Set Dates |  |
| ☐ Select location with adequate meeting facilities and parking. | Host area |
| ☐ Decide who plans with hotel: | Host area |
| ☐ Select Registration District: | Host area |
| ☐ Select a host district to arrange for a hospitality room: | Host Area |
| ☐ Select a district to coordinate the auction: |  |
| # One Year in advance |  |
| ☐ Host area appoints a Program Committee for each meeting, consisting of representatives from: - Host area - SSCC - MASCD ED - MASCD President - MD Soil Conservation Leaders Assn. - Suggested: NRCS, MDA, Extension |  |
| ☐ Identify if tours will be held | Host area |
| ☐ Determine responsibility for providing secretarial support services | Host area |
| # January- February |  |
| Awards: ☐ Revise award forms and send out to DMs. (Feb-March) ☐ Ask MASCD President about President’s Award. (Feb-March) |  |
| ☐ Recommend a change in the registration fee, if needed, to be set by the BOD | Host area |
| ☐ Share registration materials with registration district. |  |
| Agenda: Program Committee determines the number of events to be coordinated into the program ☐ Agency Meetings (NRCS, DM, Extension, SSCC) ☐ Resource Committee Meetings (Administrative and Technical) ☐ Area Meetings ☐ Maryland Soil Conservation Leaders Association ☐ Full Membership Meeting ☐ Board of Directors Meeting | Program Committee |
| ☐ Develop a theme for the meeting. Select topics and speakers to compliment the theme. Usually have a speaker at one meal function and/or the banquet. |  |
| ☐ Nominating committee prepares to recommend a slate of officers at March BOD Meeting in odd years. |  |
| # March |  |
| Reach out to Committees: ☐ Finance Committee shall prepare a budget for the BOD Meeting that includes dues. ☐ Policy Development Committee (Executive Committee, Chairs of MASCD resource committees, partner agencies) meet after March and October BOD meetings to provide guidance on issues to be addressed at upcoming MASCD meetings. ☐ Administrative Committee Chair ☐ Technical Committee Chair ☐ Resolutions Committee- check in regarding new resolutions to consider or revisions |  |
| Reach out to Districts to nominate committee members and officers: ☐ Nominating Committee (Elections in Odd Years; Nominating Com. established in Even Years) ☐ Bylaws and Operating Committee ☐ Legislative Committee ☐ Long-Range Strategic Planning Committee ☐ NACD Representative (Odd-numbered years; Usually past president for NACD Board Member and current president for alternate) |  |
| ☐ Policy Development Committee meets after March BOD Meeting. |  |
| # April |  |
| Hotel: ☐ Work with Area to finalize contract with the hotel. (President signs) Pay attention to clauses and guarantees, most hotels can be flexible. Don't put MASCD in a position of paying for unused rooms. Avoid paying any meeting room rentals. (April 30) ☐ Send MASCD State Tax letter. ☐ Send draft program to hotel. ☐ Determine use of any complimentary rooms (hospitality room, typing room, etc.) ☐ Coordinate welcomes, invocations, color guards, coffee break sponsors, etc. ☐ Select a variety of meals throughout the event (two per meal?) | Host Area |
| Agenda: ☐ Identify outside speakers ☐ Contact areas to start working on their agendas ☐ Coordinate with SSCC on Training Session ☐ Coordinate with DMs on Meeting Topics |  |
| # May |  |
| ☐ Convene Awards Committee to select recipients. |  |
| ☐ Send out registration materials (May 1), including: - President’s Invitation letter - Meal reservations form - Hotel reservations information/form - Draft Agenda | Host area |
| ☐ Registration deadline? |  |
| # June |  |
| Committees: ☐ Send updated Policy Book to Resolutions Committee ☐ Program Committee will arrange with Awards Committee Chair for award presentations during the meeting. |  |
| Awards: ☐ Notify DMs of award winners ☐ Order frames for awards (include 2 extra) |  |
| ☐ Identify any equipment needs- computers, projectors, printers for typing room, etc. |  |
| # July (1 Month – 1 Week Before) |  |
| ☐ Hotel room block deadline: August 1 Cutoff Date |  |
| ☐ Notify hotel of guaranteed number for each meal as arranged. | Registration District |
| ☐ Registration list to Registration District for name badges |  |
| Printed Materials ☐ Finalize and print programs ☐ Print Evaluation Forms ☐ Name Badges (include speakers) ☐ Name signs for Board Meeting |  |
| Awards ☐ Get checks cut to hand out for MAFC District of the Year and Conservation Teacher Awards. ☐ Create Banquet Program |  |
| # Week Before |  |
| ☐ Reminder to presenters ☐ Reminder to registrants |  |
| ☐ Prepare a binder for president with meeting agendas, speaker bios, speaking notes, financials and run-of-show |  |
| Hotel: ☐ Review program and meeting room setup requirements with hotel. ☐ Become familiar with meeting facilities- room locations, light and sound controls. ☐ Have hotel assign one person to call for assistance. |  |
| Packing List ☐ Gavel and Name Tents for BOD ☐ Programs (Meeting Program and Awards Banquet) ☐ Baskets and signs to collect meal tickets ☐ AV Backup - Projector - Screen - Extra Computer - Extension Cord - Duck Tape ☐ Office Supplies for Registration Desk - Paper - Stapler/staples - Scotch tape - Memory sticks - Pens - Pencils - Paper clips - Highlighter - Scissors - Blank Name Tags - Lanyards and Name Tag Holders - Eyeglass Repair Kit - First Aid Kit |  |
| # During Event |  |
| ☐ Set up display |  |
| ☐ Check room setups and AV |  |
| ☐ Organize head table with signs and name tags |  |
| ☐ Assign a person (President?) to meet VIPs, review program with them and introduce them to some of the MASCD officers. |  |
| ☐ Post on social media- Facebook, Twitter, Instagram |  |
| ☐ Meet with hotel and registrations district to check and pay bills | Meeting coordinator |
| ☐ Record of attendance for each event and send to President. |  |
| ☐ Items that need to be addressed during the meeting per operating rules and required actions checklist: - BOD arranges for an audit and identify a committee of the board members to present at the October BOD meeting - Adopt the budget - Set membership dues - Nominating Committee elected in even years; Elections for officers in odd years - In odd years, designate two MASCD members to serve as the member and alternate for NACD |  |
| # After Event |  |
| ☐ Send out and review evaluations |  |
| ☐ Post-event email to participants with link to evaluation survey, meeting materials and presentations |  |
| ☐ Thank you card/letter for speakers/hosts/panelists |  |
| ☐ Press Release |  |
| ☐ Report at October BOD Meeting |  |
| ☐ President appoints: - A temporary chairperson for the Nominating Committee (even years) - Chairpersons for the 5, five member committees, and “may appoint” advisors - Supervisors to fill vacancies until next area meeting - Budget and Finance Committee and select a chairperson - Chairperson and recorder for both of the resource committees - Chairperson for Annual Meeting Planning Committee |  |
| ☐ Update MASCD Manual with Committee Appointments, Resolutions, Changes to Operating Rules or Bylaws, etc. | ED, Admin |
| ☐ Mail checks and cash from event to bookkeeper | ED |
| ☐ Follow up on action items identified at the meeting | ED |
| ☐ Date for post-event committee meeting: |  |

C. ITEMS TO DISCUSS WITH HOTEL MANAGEMENT

- Number and capacity of meeting rooms (need 1 with a capacity of 200, 2 with a minimum capacity of 100, and 5 area meetings minimum capacity of 40, 50 for SSCC and Board of Directors meetings, 150 for breakfast and lunch, 275 for banquets). Charges for meeting space (usually free). Meeting room arrangement/accessibility.

- Sleeping Rooms

  - Number available (check with Executive Director for typical number of rooms used).

  - Room rates, charges for children, charge for extra person in room.

  - Local taxes on rooms and meals, State tax exemption.

  - Room deposit requirements.

  - Complimentary room policy (usually 1 per 50 rooms).

- Food service available for non-group meals.

- Group meal facilities:

  - Copies of menus with prices

  - Advance guarantee policy

  - Check variety of selections and price ranges

  - Ensure that milk is available upon request

- Charges for coffee breaks

- Policy on use of a room as a hospitality room with food and drinks brought in.

- Arrangements for typing room.

- Availability of, and charges for:

  - Audiovisual equipment, loud speaker, etc.

  - Flowers, favors, etc.

- A draft program should be sent to the hotel in advance of the meeting to assure that all meeting facilities are provided at the correct times.

MARGUERITE’S MASCD AM CHECKLIST

Work on certificates (once award names received)

Work on awards brochure

Order nameplate

Lynne order frames

Gray Granite paper

Name badges (include speakers, go thru brochure/agenda)

Bank forms?

General Meetings

Tool kit (with hammer & screwdriver)

Agendas (300±)

Banquet Program (250±)

Name Badges (plus extra blank)

Financials (40)

Gavel

Election Ballots

Association Manual

Meeting file

Policy books (6)

MASCD Note Spiral Binder

Meeting Room Signs (check for completeness)

Board Meeting name signs (check for completeness)

Head Table Name Tags

Typing Room

Printer/Copier

Paper

Extra Toner

USB Cable

Disc with driver

Memory Stick

- Opening & General Session (for president)

- Awards Write up

- Certificates (Publisher)

- Brochure & Program

- Resolution format in PowerPoint

- Registrant List (Excel)

- Survey

- Documentation from Hotel

- Award Template

- Board Meeting Agendas (1st and 2nd Meetings)

Awards

3 checks for MAFC outstanding district

Awards Certificates (check for accuracy)

Frames (include 2 extras)

Nameplate for district attendance recipient

Service Pins (check for accuracy)

2 lists of Service Pin recipients (do not staple)

Awards Write up

Extra Awards paper

MAFC Entries to distribute

Award folders (MASCD and MAFC)